## How to Use
BOM Master List Template — How to Use
For every new project: copy this file, rename it <ProjectCode>_BOM_Rev0.xlsx, fill the header and the Lists sheet. Never start from an old project file.
WHO | FILLS
Engineering (blue) | Sub-Assembly, Discipline, Description, Part No, Manufacturer, Category, Qty/Set, Multiple, Unit, Make/Buy, Drawing/Rev, NSW Part No, PIC, Issue & Required Date
Purchasing (green) | Status, Supplier, PR, PO, PO Date, ETA, DO/Invoice, Qty Received, Received Date, Unit Price
Assembly (orange) | Qty Issued, Taken By, Date — when parts leave store to the line
Auto (navy) | Item No, Total Qty, Total Price, Flag — don't type
STATUS | Same legend as before — now a dropdown, and the row colours itself
Not Finalized
Finalized – Not Purchased
Purchased – Not Received
Received
NSW Purchased
New Request to NSW
Cancelled
FLAG | MEANING
NO QTY | Qty/Set blank — engineer to fill
NO PART NO | Buy item without manufacturer P/N
OVERDUE | ETA passed, not received — chase supplier
LATE vs REQ | Supplier ETA is after the Required Date — escalate
NEED PR | Finalized but no PR raised
SHORT | Received less than Total Qty
RULES
1 | One row per part. Don't insert section/title rows — use the Sub-Assembly dropdown.
2 | Never delete a row — set Status to Cancelled.
0 | Setup: fill header (Project Name, Code, Customer) + rename sub-assemblies in Lists.
3 | Design change → update Drawing Rev, note it in Remarks, add a line in Revision Log.
4 | Update 'Last Updated' (BOM sheet, F6) every Monday by 12pm.
6 | Don't rename or move columns — the file is designed to import into the Nix Project Tracker.
5 | Customer View has no prices — still Paste Values before sending.
Example row (format only — enter real rows in BOM sheet):
Item | Sub-Assembly | Discipline | Description | Manufacturer Part No. | Manufacturer | Category | Qty / Set | Multiple | Total Qty | Unit | Make / Buy | Drawing No. / Rev | NSW Part No. | Engineer PIC | Issue Date | Required Date | Status | Supplier | PR No. | PO No. | PO Date | ETA | DO / Invoice No. | Qty Received | Received Date | Unit Price (RM) | Total Price (RM) | Qty Issued | Taken By | Issue Date (Assy) | Flag | Remarks
120-01 | 120 SINGULATOR | Mechanical | CYLINDER | CDU16-25D-M9BL | SMC | Pneumatic | 2 | 1 | 2 | Pcs | Buy | XX-120-005 Rev A |  | HC | 01-Oct-26 | 20-Oct-26 | Purchased – Not Received | Supplier name | PR-0123 | PO-0456 | 03-Oct-26 | 15-Oct-26 |  |  |  | 85 | 170 |  |  |  |  | Pick-up cylinder

## BOM
BOM Master List — Project Template
Blue = Engineering · Green = Purchasing · Orange = Assembly · Navy = auto (don't type). One row per part, no section rows — pick Sub-Assembly from the dropdown instead.
Project Name: |  |  |  | Originator: |  |  |  |  | BOM value (RM): | 0
Project Code: |  |  |  | Approval:
Customer: |  |  |  | Revision: | 0
Scope: | All disciplines |  |  | Last Updated:
AUTO | ENGINEERING | [7 empty] | AUTO | ENGINEERING | [6 empty] | PURCHASING | [9 empty] | AUTO | ASSEMBLY |  |  | AUTO | ENGINEERING
Item | Sub-Assembly | Discipline | Description | Manufacturer Part No. | Manufacturer | Category | Qty / Set | Multiple | Total Qty | Unit | Make / Buy | Drawing No. / Rev | NSW Part No. | Engineer PIC | Issue Date | Required Date | Status | Supplier | PR No. | PO No. | PO Date | ETA | DO / Invoice No. | Qty Received | Received Date | Unit Price (RM) | Total Price (RM) | Qty Issued | Taken By | Issue Date (Assy) | Flag | Remarks

## Progress
BOM Progress Dashboard
Auto from BOM. Finalized = any status past 'Not Finalized'. Ordered = Purchased–Not Received / Received / NSW Purchased. Cancelled excluded. Cost columns are INTERNAL.
OVERALL
BOM lines |  | Finalized |  | Ordered |  | Received |  | Overdue |  | Lines with flags
0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 0% |  | 0% |  | 0%
By Sub-Assembly
Group | Lines | Finalized | % Final | Ordered | % Ordered | Received | % Rcvd | Overdue | Flags (any) | Value (RM)
110 BASE & STRUCTURE | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
120 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
130 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
140 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
150 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
160 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
170 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
180 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
190 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
200 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
210 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
220 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
230 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
240 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
250 (rename) | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
TOTAL | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
By Discipline
Group | Lines | Finalized | % Final | Ordered | % Ordered | Received | % Rcvd | Overdue | Flags (any) | Value (RM)
Mechanical | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Electrical | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Pneumatic | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Software / Vision | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Others | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
TOTAL | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
By Category
Group | Lines | Finalized | % Final | Ordered | % Ordered | Received | % Rcvd | Overdue | Flags (any) | Value (RM)
Fabricated Part | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Std Mechanical | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Pneumatic | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Vacuum | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Motion / Actuator | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Electrical / Control | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Sensor | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Vision | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Safety | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
Consumable / Others | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0
TOTAL | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0

## Customer View
Bill of Materials
Auto from BOM — no supplier, PR/PO, price or internal remarks. Copy → Paste Values into a new file before sending to Teleflex.
Item | Sub-Assembly | Discipline | Description | Manufacturer Part No. | Manufacturer | Total Qty | Unit | Drawing No. / Rev | Status | ETA

## Revision Log
Revision Log
Add a line every time the BOM is re-issued to Teleflex.
Rev | Date | Changes | By | Approved

## Lists
Dropdown Lists
Yellow = edit per project. Format: <3-digit no.> <NAME>, e.g. 120 SINGULATOR. Add rows at the bottom of the list if needed (up to 15).
Sub-Assembly | Discipline | Category | Status | Make/Buy | Unit
110 BASE & STRUCTURE | Mechanical | Fabricated Part | Not Finalized | Buy | Pcs
120 (rename) | Electrical | Std Mechanical | Finalized – Not Purchased | Make (Fabricate) | Set
130 (rename) | Pneumatic | Pneumatic | Purchased – Not Received | Customer Supplied | Mtr
140 (rename) | Software / Vision | Vacuum | Received |  | Lot
150 (rename) | Others | Motion / Actuator | NSW Purchased |  | Roll
160 (rename) |  | Electrical / Control | New Request to NSW
170 (rename) |  | Sensor | Cancelled
180 (rename) |  | Vision
190 (rename) |  | Safety
200 (rename) |  | Consumable / Others
210 (rename)
220 (rename)
230 (rename)
240 (rename)
250 (rename)